## Worksheet
Task ID | Project Id | Task Title | Task Created | Task Creator | Task Client | Project_Title | Task Start Date | Task Due Date | Task Decription | Task Priority | Task Status | Task MileStone | Task Billable Status | Task Billing | Task Recurring | Task_Recurring_Duration | Task_Recuuring_Finished
131 | 13 | Latest Happening: We have three news and this third news is also shown at the top of the home page but we couldn’t see it in this section. | 05-13-2024 | Muhammad Idrees | MT Academy | MT Academy Development | 2024-05-13 | 2024-05-22 | Latest Happening: We have three news and this third news is also shown at the top of the home page but we couldn’t see it in this section. | Normal | Completed | Planning | not_invoiced | yes | no |  | no
126 | 13 | Empowering tomorrow learn more button | 05-13-2024 | Muhammad Idrees | MT Academy | MT Academy Development | 2024-05-13 | 2024-05-21 | The Learn More button goes back to the home page. It has to open the Academics page. | Normal | Completed | Planning | not_invoiced | yes | no |  | no
124 | 13 | Admissions, Academics and latest from us must have read more button that leads to their pages. | 05-13-2024 | Muhammad Idrees | MT Academy | MT Academy Development | 2024-05-13 | 2024-05-22 | Admissions, Academics and latest from us must have read more button that leads to their pages. | Normal | Completed | Planning | not_invoiced | yes | no |  | no
123 | 13 | Homepage banner learn more link should lead to | 05-13-2024 | Muhammad Idrees | MT Academy | MT Academy Development | 2024-05-13 | 2024-05-13 | The Learn More button leads to this Link: https://mehrschool.com/news-events/media-gallery-mbs-mis | Normal | Completed | Planning | not_invoiced | yes | no |  | no
121 | 17 | Drivers Module | 05-08-2024 | Muhammad Idrees | Digital Poin8 | Lets Tourz CRM | 2024-05-09 | 2024-05-10 | Need to have following fields for driver module Name Email Phone Location/Area | Normal | Completed | Planning | not_invoiced | yes | no |  | no
120 | 17 | Pickup Module | 05-08-2024 | Muhammad Idrees | Digital Poin8 | Lets Tourz CRM | 2024-05-08 | 2024-05-09 | Cofirmation poup with following options: Driver assignment from driver module Pickup date editable Pickup time editable Pickup location | Normal | Completed | Development | not_invoiced | yes | no |  | no
110 | 16 | Expenses - Export to Excel | 04-04-2024 | Anees Ur Rasool | Digital Poin8 | DP8 Invoices |  |  | Export feature required on filtered data of expenses (Export to Excel) |  | Completed | Development | not_invoiced | yes | no |  | no
109 | 16 | Show VAT - Custom Field in the table under Expenses section | 04-04-2024 | Anees Ur Rasool | Digital Poin8 | DP8 Invoices |  |  | Show VAT - Custom Field as a column in the table (with data) under Expenses section |  | Completed | Development | not_invoiced | yes | no |  | no
108 | 16 | PDF Footer to be updated | 04-04-2024 | Anees Ur Rasool | Digital Poin8 | DP8 Invoices | 2024-04-04 |  | PDF Footer to be updated with following text:Make all checks payable to Digital Point Web Design L.L.C.For any query, please contact: TEL# +971 4 405 4144. |  | Completed | Development | not_invoiced | yes | no |  | no
107 | 16 | Line spacing as per given format | 04-04-2024 | Anees Ur Rasool | Digital Poin8 | DP8 Invoices | 2024-04-04 |  | Line spacing as per given format |  | Completed | Development | not_invoiced | yes | no |  | no
106 | 16 | Font size and font family to match with the required format | 04-04-2024 | Anees Ur Rasool | Digital Poin8 | DP8 Invoices | 2024-04-04 |  | Font size and font family to match with the required format. Required format uploaded in files section of this project |  | Completed | Development | not_invoiced | yes | no |  | no